## Slide 1: DLH Projects Status Report PMO Weekly Report from: 05\06\22 to 09\06\22
DOCUMENT USAGE: This document is for internal use only. This template may be customized according to specific project needs and when appropriate, based on needs.

## Slide 2: Table of Contents
1
Executive summary
2
Projects Health Overview
3
Resource Planning
Summarize the key status indicators for the projects as a whole
Provides information on the current status for each project
Distribute the team among of the projects
This PMO Health check is divided into 3 sections:

## Slide 3: Executive summary projects portfolio
Y
A
R
G
Under control
To be monitored closely
Requires immediate attention
Pause work while deploying corrective actions
Projects Complete
Q1 22
Q2 22
Q3 22
Q4 22
Today
CITC Data Dictionary
S
B
R
$ 350K
Feb
March
April
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Projects in flight
Projects Pipeline
MA’ADEN
S
B
R
$ 600K
MHRSD
S
B
R
$ 600K
Contact Centers CO
$
S
B
R
MMIR
$
S
B
R
SABIC
$
S
B
R
HSBC
$
STC Corporate Analytics & Data (CAD) Sector Audit
$
S
B
R
S
B
R
CITC DG
$
S
B
R

## Slide 4: Resource Utilization 2022
Chart: 
| 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805
Actual | 0.33 | 0.58 | 0.6 | 0.63 | 0.64 | 0.68 | 0.65 | 0.62
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8

## Slide 5: Financial Dashboard
Chart: 
| Q1 | Q2 | Q3 | Q4
Invoiced | 90 | 95 | 80 | 85
Planned | 85 | 90 | 80 | 75
Chart: 2022 Target: 17.5 M
| Remaining | Invoiced | Collected
22 Target 17.5 M | 8.2 | 3.2 | 1.4

## Slide 6: DLH Invoices
Invoice | Manager | Amount | Due | Project | Status | Comments
Payment 1 (Payment Description) | Ahmad Abdullah | Xxxxx$ | mm\2022 | Project XYZ | Invoiced | 
Payment 2 (Payment Description) | Abdullah Ahmad | Xxxxxx$ | mm\2022 | Project XYZ | Eetmad KPMG upload | 
Payment 3 (Payment Description) | Omar Saad | Xxxxxx$ | mm\2022 | Project XYZ | Pending | Required Attention
Payment 4 (Payment Description) | Mohammad Saed | Xxxxxx$ | mm\2022 | Project XYZ | Collected | 
Payment 5 (Payment Description) | Ahmad Abdullah | Xxxxxx$ | mm\2022 | Project XYZ | Invoiced | 
Payment 6 (Payment Description) | Abdullah Ahmad | Xxxxxx$ | mm\2022 | Project XYZ | Eetmad Client upload | 
Payment 7 (Payment Description) | Omar Saad | Xxxxxx$ | mm\2022 | Project XYZ | Pending | Required Attention
Payment 8 (Payment Description) | Mohammad Saed | Xxxxxx$ | mm\2022 | Project XYZ | Collected | 
Total: 17.5$ M
Invoiced: 8.5$ M
Collected: 17.5$ M
Etmad: 17.5$ M
Pending: 17.5$ M

## Slide 7: CITC Project Health
Other Key updates & notes
Note: Client is not satisfied with the awareness material
Note: Team is still waiting for stakeholder comments
Note: Risks need to be reviewed
END DATE
May 2022
START DATE
Nov 2021
Apr | May |  | Jun | Jul. | Aug | Sep | Oct
Activity 1
Activity 2
Activity 3
Project Health
Progress
There is a dependency on stakeholders' comment
Dependency
Risk: KPMG’s invoice won’t be paid fully
Risk
Today
Project Manager
Faris Abomelha
Sponsor
Maz Hussain
Planned: 100%
95%
Chart: Expenses
| Consumed | Remaining
Sales | 8.2 | 3.2
Chart: 
| Risks | Issues
M | 1 | 1

## Slide 8: Week Planned Activities
Action | Owner
Working on stakeholders comments | Faris
Action | Owner
If comments are finalized then project can proceed to completeness | Faris
    Next Week Activities
    Key Planned Activities

## Slide 9: Risks or issues
# | Risk or Issue | Priority | Plan | Owner
1 | Client may not pay KPMG full invoice amount | Remediation | Finalize comments as soon as possible | Faris
2 | Client is not satisfied with the awareness material | Remediation | Take feedback from client and check feasibility | Faris

## Slide 10: MA’Aden Project Health
Other Key updates & notes
Team is in process of finalizing the business case as well as steering committee material
Socialize next week findings with internal stakeholders
Finished the data maturity assessment
Staged target route was created
Team has finished putting a staged and target states to expedite value realization
END DATE
June 2024
START DATE
Nov 2021
Apr | May |  | Jun | Jul. | Aug | Sep | Oct
Activity 1
Activity 2
Activity 3
Project Health
Progress
No dependency but leadership is required to push the budget increase proposal
Dependency
The project is under-resourced from the client side and more budget to KPMG is required to get more resources
Risk
Today
Project Manager
Maryam Al Bahri
Sponsor
Miguel Neves
Planned: 10%
5%
Chart: Expenses
| Consumed | Remaining
Sales | 8.2 | 3.2
Chart: 
| Risks | Issues
M | 1 | 0
N/A

## Slide 11: Week Planned Activities
Action | Owner
Waiting for client resourcing | Maryam
Action | Owner
Waiting for client resourcing | Maryam
    Next Week Activities
    Key Planned Activities

## Slide 12: Key Accomplishments
# | Accomplishment Description
1 | Finalized the data maturity assessment
2 | Created a staged target route
3 | Finalized staged and target states to expedite value realization
4 | Created a roadmap that will ensure meeting the target stages (Stage 1 is a priority)

## Slide 13: Risks or Issues
# | Risk or Issue | Priority | Plan | Owner
1 | Client/KPMG under-resourcing | High | Push on KPMG proposal | Maryam

## Slide 14: MHRSD Project Health
Other Key updates & notes
KPMG team will finalize wave 1 in august
Dashboard model documentation was done
END DATE
March 2024
START DATE
Dec 2021
Apr | May |  | Jun | Jul. | Aug | Sep | Oct
Activity 1
Activity 2
Activity 3
Project Health
Progress
None Noted
Dependency
No risks identified
Risk
Today
Project Manager
Faris Abomelha
Sponsor
Kaushal Dayal
Planned: 20%
20%
Chart: Expenses
| Consumed | Remaining
Sales | 8.2 | 3.2
Chart: 
| Risks | Issues
H | 0 | 0
M | 0 | 0
L | 0 | 0
N/A

## Slide 15: Week Planned Activities
Action | Owner
Dashboard Documentation Optimization | Faris
Data Model Documentation | Faris
Action | Owner
Gap analysis | Faris
    Next Week Activities
    Key Planned Activities

## Slide 16: Key Accomplishments
# | Accomplishment Description
1 | Dashboard model documentation

## Slide 17: Risks or Issues
# | Risk or Issue | Priority | Plan | Owner
1 | No risks or issues identified |  |  | 

## Slide 18: STC Corporate Analytics & Data (CAD) Sector Audit
Other Key updates & notes
Finalizing the maturity assessment report
END DATE
May 2022
START DATE
Feb 2022
Apr | May |  | Jun | Jul. | Aug | Sep | Oct
Activity 1
Activity 2
Activity 3
Project Health
Progress
None Noted
Dependency
No risks identified
Risk
Today
Project Manager
Thomas Young
Sponsor
Maz Hussain
Planned: 100%
99%
Chart: Expenses
| Consumed | Remaining
Sales | 8.2 | 3.2
Chart: 
| Risks | Issues
H | 0 | 0
M | 0 | 0
L | 0 | 0
N/A

## Slide 19: Week Planned Activities
Action | Owner
No Planned activities | Shaikhah
Action | Owner
No Planned activities | Shaikhah
    Next Week Activities
    Key Planned Activities

## Slide 20: Key Accomplishments
# | Accomplishment Description
1 | Dashboard model documentation

## Slide 21: Risks or Issues
# | Risk or Issue | Priority | Plan | Owner
1 | No risks or issues identified |  |  | 

## Slide 22: Key Accomplishments
# | Accomplishment Description
1 | Conducted the audit against NDMO controls for the 9 CAD sector departments, and reviewed the existing data management maturity assessment framework and implementation status of the initiatives that feed into the maturity assessment, and provided recommendations

## Slide 23: Contact Centers CO
Other Key updates & notes
KPMG India are in discussions to scope for phase 3
Delay in accepting deliverables is due to CCC challenges in validating data
END DATE
July 2022
START DATE
Jan 2022
Apr | May |  | Jun | Jul. | Aug | Sep | Oct
Activity 1
Activity 2
Activity 3
Project Health
Progress
None Noted
Dependency
Delay on invoice sign-off
Risk
Today
Project Manager
Saad Abunnab
Sponsor
Shahbaz Haque
Planned: 100%
85%
Chart: Expenses
| Consumed | Remaining
Sales | 8.2 | 3.2
Chart: 
| Risks | Issues
M | 1 | 1
N/A

## Slide 24: Week Planned Activities
Action | Owner
Prepare for training | Saad
Finalize Testing | Saad
Action | Owner
Follow up on payments | Saad
Discuss with KPMG India on next steps and risk mitigation plan | Saad
    Next Week Activities
    Key Planned Activities

## Slide 25: Key Accomplishments
# | Accomplishment Description
1 | N/A

## Slide 26: Risks or Issues
# | Risk or Issue | Priority | Plan | Owner
1 | It's unclear KPMG KSA interest in pursuing phase 3 | M | Follow-up | Saad
2 | Delay on invoice sign-off | M | Follow-up | Saad

## Slide 27: MMIR Project Health
Other Key updates & notes
END DATE
January 2023
START DATE
June 2022
Apr | May |  | Jun | Jul. | Aug | Sep | Oct
Activity 1
Activity 2
Activity 3
Project Health
Progress
Dependency
Risk
Today
Project Manager
Asiminia Asimota
Sponsor
Maz Hussain
Planned: 0%
0%
Chart: Expenses
| Consumed | Remaining
Sales | 8.2 | 3.2
Chart: 
| Risks | Issues
L | 0 | 0

## Slide 28: SABIC
Other Key updates & notes
END DATE
December 2022
START DATE
June 2022
Apr | May |  | Jun | Jul. | Aug | Sep | Oct
Activity 1
Activity 2
Activity 3
Project Health
Progress
Dependency
Risk
Today
Project Manager
Thomas Young
Sponsor
Maz Hussain
Planned: 0%
0%
Chart: Expenses
| Consumed | Remaining
Sales | 8.2 | 3.2
Chart: 
| Risks | Issues
L | 0 | 0

## Slide 29: Next Week Resource Planning
Resource | % | Sunday |  | Monday |  | Tuesday |  | Wednesday |  | Thursday | 
Haque, Shahbaz | 100% |  |  |  |  |  |  |  |  |  | 
Young, Thomas | 100% |  |  |  |  |  |  |  |  |  | 
Hnaity, Omar | 100% |  |  |  |  |  |  |  |  |  | 
Neves, Miguel | 100% |  |  |  |  |  |  |  |  |  | 
Abuennab, Saad | 100% |  |  |  |  |  |  |  |  |  | 
Abomelha, Faris | 100% |  |  |  |  |  |  |  |  |  | 
Alamasi, Wafa | 100% |  |  |  |  |  |  |  |  |  | 
Simota, Asimina | 100% |  |  |  |  |  |  |  |  |  | 
Shehab, Mohammad | 100% |  |  |  |  |  |  |  |  |  | 
… |  |  |  |  |  |  |  |  |  |  | 
Overall Planned Utilization: 100%
Project Beta
Business Development
Project X
Project Y
Project Alpha
Project Z
Administration
Off
Project Alpha
100%
100%
100%
100%
100%
100%
100%
100%
100%
Use the Other Sheet

## Slide 30: Appendix A – Risk Register
No. | Risk Description | Probability (H/M/L) | Effect (H/M/L) | Planned Mitigation
1 | CITC - Client may not pay KPMG's full invoice amount | M | M | Strategic discussion and negotiation with the client
2 | MA’Aden - The project is under-resourced from the client side and more budget to KPMG is required to get more resources | M | M | Leadership to push for budget increase
3 | Delay on invoice sign-off | M | M | Follow up with client
4 |  |  |  | 

## Slide 31: Appendix B – Issues Log
Issue Description | Date Raised | Owner | Agreed Action | Action Status | Date Closed
CITC - Client is not satisfied with the awareness material | 8 June | Faris | To be finalized with project sponsor | N/A | N/A
CCO -It's unclear KPMG KSA interest in pursuing phase 3 | 9 June | Saad | To be discussed with project sponsor | N/A | N/A

## Slide 32: Appendix C – Action Register
Action Item Register |  |  |  |  |  |  |  |  |  | 
No. | Action item | Description | Status / ongoing activities | Sub-project | Owner / responsibility | Priority | Date identified | Due date | Date closed | Status

## Slide 33: Thank you